PORTION TRACK

Professional Feature Proposal & Estimate

Optional Steps Integration via Apple Health & Google Health Connect

| Prepared for Amy / Portion Track | Estimate 75–80 hours | Duration ~10 working days | Version Steps Integration v1 |
| --- | --- | --- | --- |

# 1. Executive Summary

Portion Track already helps users build healthier eating habits through simple portion tracking. Many users also walk daily, but the app currently requires manual exercise logging. This proposal adds an optional link to Apple Health (iOS) and Health Connect (Android) so today’s steps can appear automatically in the app.

The feature is designed to increase product value and daily engagement while preserving Portion Track’s core privacy model: health step data is read on the user’s device only and is not uploaded to Portion Track servers.

Recommended decision: Approve Steps Integration v1 at 75–80 hours.

# 2. Value & Benefits

Below are the primary benefits this feature delivers for users and for Portion Track.

- Automatic activity tracking — users no longer need to remember to log that they walked.

- Lower friction daily use — the app works with data the phone already collects.

- Stronger habit loop — food portions and movement appear together in one daily view.

- Better fit for walkers — a large share of wellness users rely on walking, not gym workouts.

- Higher retention potential — users return to see progress they did not have to enter manually.

- Complements existing exercise logging — manual workouts stay; steps fill the gap for everyday movement.

- Privacy-aligned differentiation — value is added without collecting health data on your servers.

- Clear marketing story — “Link Apple Health / Google steps” is easy to explain on the website and store listings.

- Supports your mission — simple, sustainable habits without calorie obsession or complex fitness tracking.

- Competitive parity — many habit and wellness apps offer health-linked steps; Portion Track currently does not.

- Optional by design — users who prefer not to connect are unchanged; no forced permissions.

- Cross-platform consistency — same benefit on iPhone (Apple Health) and Android (Health Connect).

## What this is not

This is not a calorie burner, medical diagnosis tool, or fitness social network. It does not replace manual exercise logging. It is a focused, optional steps layer that makes everyday movement visible with minimal effort.

# 3. Proposed Solution

## 3.1 User experience (v1)

- User chooses Connect Apple Health or Connect Health Connect from Settings or a light prompt on the tracking experience.

- System permission dialog appears; user can allow or deny.

- If allowed, today’s step count is shown in the daily tracking experience.

- User may set an optional simple daily step goal.

- User may disconnect at any time; the rest of the app continues to work unchanged.

## 3.2 Technical approach

- iOS: Apple HealthKit — read steps only, on device.

- Android: Health Connect — read steps only, on device.

- Preferences (linked / not linked, optional goal) stored locally with existing app storage patterns.

- No new backend collection of step data for v1.

## 3.3 Privacy & compliance

- Permission is explicit and optional.

- Step data remains on device; not sent to Portion Track servers.

- Privacy Policy and store permission text updated to state this clearly.

- English and Spanish UI included for launch consistency.

# 4. Scope

## In scope (v1)

- Connect / disconnect Apple Health and Health Connect

- Read and display today’s steps

- Optional daily step goal

- Today / tracking UI integration and Settings status

- EN + ES localization

- Privacy Policy notes and App Store / Play permission copy

- QA on iOS and Android; release-candidate build

## Out of scope (v1)

- Heart rate, sleep, workouts sync, GPS routes

- Cloud backup or analytics of health data

- Social sharing, leaderboards, coaching AI

- Replacing or removing manual exercise logging

# 5. Detailed Estimate — How This Will Be Achieved

Work is organized into six phases. Each phase lists activities and the concrete deliverable produced. Total effort: 75–80 hours across approximately 10 working days.

| Phase | Workstream | Hours | Schedule |
| --- | --- | --- | --- |
| Phase 1 | Discovery, UX & Privacy Framing | 8 | Day 1 |
| Phase 2 | iOS Implementation (Apple Health / HealthKit) | 16 | Days 2–3 |
| Phase 3 | Android Implementation (Health Connect) | 16 | Days 4–5 |
| Phase 4 | Product Integration (Today Experience & Goals) | 16 | Days 6–7 |
| Phase 5 | Localization, Compliance & Store Readiness | 8 | Day 8 |
| Phase 6 | QA, Hardening & Handoff | 12–16 | Days 9–10 |
| TOTAL | Steps Integration v1 | 75–80 | ~10 working days |

## Phase 1: Discovery, UX & Privacy Framing (8 hours · Day 1)

Activities

- Define the end-to-end user journey: discover feature → connect → grant permission → view today’s steps → optional goal → disconnect.

- Map where steps appear relative to existing Exercise logging (no replacement of current flow).

- Write privacy and permission copy for in-app, Privacy Policy update notes, and store listing language.

- Confirm v1 acceptance criteria and non-goals with stakeholder sign-off.

Phase deliverable: Signed-off feature brief, screen list, privacy wording draft, acceptance criteria.

## Phase 2: iOS Implementation (Apple Health / HealthKit) (16 hours · Days 2–3)

Activities

- Add HealthKit capability, Info.plist usage descriptions, and EAS/config plugin setup.

- Implement secure on-device read of daily step count.

- Build Connect / Disconnect UI, permission granted/denied/retry states, and local preference storage.

- Device testing on iPhone for permission and data accuracy.

Phase deliverable: Working iOS connect flow; today’s steps readable from Apple Health on device.

## Phase 3: Android Implementation (Health Connect) (16 hours · Days 4–5)

Activities

- Integrate Health Connect permissions and step-read APIs (current Google standard).

- Handle Health Connect not installed / unavailable with clear user guidance.

- Mirror iOS Connect / Disconnect experience for Android.

- Device testing on Android for permission and data accuracy.

Phase deliverable: Working Android connect flow; today’s steps readable from Health Connect on device.

## Phase 4: Product Integration (Today Experience & Goals) (16 hours · Days 6–7)

Activities

- Surface today’s step count on the main tracking experience.

- Add optional simple daily step goal (user-controlled).

- Add Settings status for linked / not linked health source.

- Implement refresh behavior, midnight reset, revoked permission, and offline-safe handling.

Phase deliverable: Steps visible in daily tracking; settings control; stable everyday behavior.

## Phase 5: Localization, Compliance & Store Readiness (8 hours · Day 8)

Activities

- Localize all new UI strings in English and Spanish.

- Finalize App Store Health / HealthKit and Play Health Connect permission justifications.

- Prepare Privacy Policy addition: on-device only, no server upload of steps.

Phase deliverable: EN/ES complete; store and privacy text ready to publish.

## Phase 6: QA, Hardening & Handoff (12–16 hours · Days 9–10)

Activities

- End-to-end QA on iOS and Android against acceptance criteria.

- Verify no step data is transmitted to backend services.

- Bug fixes, UI polish, and release-candidate build.

- Handoff notes, demo checklist, and buffer for late findings.

Phase deliverable: Release candidate build; QA checklist; Amy review package.

# 6. Day-by-Day Delivery Schedule

The schedule below shows daily ownership of outcomes so progress can be reviewed at the end of each day.

| Day | Hours | End-of-day result |
| --- | --- | --- |
| 1 | 8 | Brief, UX flow, privacy copy, and acceptance criteria ready for sign-off |
| 2 | 8 | iOS HealthKit configured; step count readable in a test build |
| 3 | 8 | iOS connect and disconnect experience complete on device |
| 4 | 8 | Android Health Connect configured; step count readable in a test build |
| 5 | 8 | Android connect and disconnect experience complete on device |
| 6 | 8 | Today screen shows live steps; optional step goal available |
| 7 | 8 | Settings status, refresh behavior, and edge cases handled |
| 8 | 8 | English and Spanish complete; store and privacy text finalized |
| 9 | 8 | End-to-end QA completed; critical bugs fixed |
| 10 | 6–8 | Release-candidate build, polish, and handoff package delivered |

# 7. Assumptions & Risks

## Assumptions

- Stakeholder feedback on Day 1 brief is provided within one business day.

- Access to TestFlight / internal Android builds remains available as today.

- Privacy Policy page can be updated when store copy is ready.

## Risks & mitigations

- Platform permission / review requirements — mitigated by early compliance text and optional-only design.

- Android Health Connect availability varies by device — mitigated with clear fallback messaging.

- Scope creep into full fitness suite — mitigated by explicit out-of-scope list in this proposal.

# 8. Investment Summary

| Item | Detail |
| --- | --- |
| Professional services estimate | 75–80 hours |
| Calendar duration | ~10 working days |
| Platforms | iOS (Apple Health) + Android (Health Connect) |
| Languages | English + Spanish |
| Privacy model | On-device read only; no server upload of steps |
| Primary output | Release-candidate app build + review package |

# 9. Approval

Please approve this proposal to proceed with Steps Integration v1 under the estimate and scope defined above.

Approved by: ____________________________     Date: ______________

Upon approval, Phase 1 begins immediately, with the Day 1 brief returned for quick confirmation before implementation continues.

Portion Track — Steps Integration v1 — Professional Estimate Proposal — 75–80 hours