PORTION TRACK

Steps (Apple Health / Health Connect)

Remaining Phases Plan

Prepared for Amy  ·  7 October 2026

# 1. Purpose

This document covers only the remaining work for the lean Steps v1 feature. Phases already completed are summarised briefly so the path to TestFlight and Google Play testing is clear.

Commitment to Amy: push after Phase 3 or 4 so there is enough to test meaningfully — not a tiny partial. Phase 4 hardening is now complete locally; next is compliance readiness, then push + builds + device QA.

# 2. Status snapshot

| Phase | Status | Notes |
| --- | --- | --- |
| 1 — Discovery | Skipped | Lean scope approved; no separate discovery package. |
| 2 — iOS | Code done | HealthKit path in app; not yet validated on iPhone / TestFlight. |
| 3 — Android | Done + tested | Health Connect connect + today’s count verified on device. |
| 4 — Product integration | Done (local) | Settings, goal, Exercise progress, EN/ES, refresh / midnight / permission edge cases. |
| 5 — Compliance & store | Remaining | Privacy policy publish + App Store / Play Console forms. |
| 6 — QA & handoff | Remaining | Git push, native builds, Amy TestFlight + Play test, sign-off. |

# 3. What is already in the app (Phases 2–4)

•  Settings → Steps: connect / disconnect, daily goal (default 8,000), today’s total

•  Exercise tab: progress bar for today only (hidden when another day is selected)

•  Read-only steps from Apple Health (iOS) and Health Connect (Android)

•  On-device only — no server upload of step data

•  English and Spanish

•  Refresh on screen focus, app foreground, and midnight day change

•  Android: Install Health Connect link when unavailable; revoked / failed-read guidance

•  Store wording draft ready (docs/health-store-wording.txt)

Code is still local only — not committed or pushed yet.

# 4. Phase 5 — Localization, compliance & store readiness

Goal: store and privacy text ready to publish so builds can pass review.

In-app EN/ES strings for Steps are already complete. Remaining work is external / console.

5.1 Activities

•  Update portiontrack.com Privacy Policy with short Steps language (read-only, on-device, not uploaded)

•  App Store Connect: HealthKit purpose + NSHealthShare usage text from store wording draft

•  Google Play Console: Health Connect READ_STEPS declaration + justification from store wording draft

•  Confirm app.json plugin strings match what will be submitted (already drafted)

•  Quick pass that Settings privacy link still points to the live policy URL

5.2 Deliverables

•  Published privacy policy section covering Steps

•  ASC / Play form fields filled (or ready to paste)

•  Confirmed in-app strings + store copy aligned (EN; ES already in app)

5.3 Suggested effort

~4–8 hours (mostly content / console; little new app code)

5.4 Owner notes

•  Privacy Policy website update may need Amy / site owner access

•  Store console submissions typically Amy for final submit; Muhammad prepares exact wording

# 5. Phase 6 — QA, builds & handoff

Goal: Amy can test a meaningful build on iPhone (TestFlight) and Android (Play internal / closed test).

6.1 Activities

•  Commit and push Steps changes to the repo (after Phase 5 wording is ready, or in parallel if agreed)

•  EAS iOS build → Amy launches TestFlight

•  EAS Android build for Play internal/closed testing → Amy reviews

•  Run QA checklist on physical devices (below)

•  Fix any blockers found in Amy’s first pass

•  Confirm billing / subscriptions were not changed by this work

6.2 Amy QA checklist

•  Fresh install → complete / bypass paywall as needed → open Settings → Steps

•  Connect Apple Health (iOS) or Health Connect (Android); grant Steps only

•  See today’s count update after walking (source app must write steps on Android)

•  Change daily goal; confirm Exercise tab progress matches

•  Exercise day selector on another day → steps card hidden; back to today → shown

•  Background app, walk, reopen → count refreshes

•  Disconnect → steps card disappears; reconnect works

•  Language EN / ES labels look correct

•  Confirm steps are not uploaded (no account health sync) — privacy promise holds

6.3 Deliverables

•  Pushed code on main (or agreed branch)

•  TestFlight build ready for Amy

•  Google Play test track build ready for Amy

•  Short QA notes / any known limitations (e.g. Expo Go not supported)

6.4 Suggested effort

~8–12 hours (builds, device QA, small fixes)

# 6. Recommended sequence

| Step | Action |
| --- | --- |
| A | Finish Phase 5: privacy policy + store wording paste-ready / published. |
| B | Push Phases 2–4 code (local Steps feature + Phase 4 hardening). |
| C | Produce iOS + Android native builds; notify Amy TestFlight + Play test are ready. |
| D | Amy physical-device QA; Muhammad fixes blockers; release when signed off. |

# 7. Explicitly out of scope (still)

•  Heart rate, sleep, workouts sync, GPS

•  Cloud backup or analytics of health data

•  Social / leaderboards / coaching AI

•  Replacing manual exercise logging

•  Expo Go support (native rebuild required)

# 8. Push / test message to Amy (when ready)

When Phase 5 is done and builds are up, a short note can be:

“Steps Phases 2–4 are pushed and builds are ready. Please TestFlight on iPhone and check the Google Play test build when convenient. Checklist: Settings → Steps → connect → walk → confirm Exercise shows today’s progress. Disconnect should hide the card.”

# 9. Approval / next action

Suggested next action: proceed with Phase 5 (privacy + store copy), then Phase 6 push and builds for Amy’s TestFlight and Play review.

Prepared by: Muhammad

Date: 7 October 2026